SOCIAL CONNECT Digital Marketing Campaign ──────────────────── WEEK 3: Performance Analysis, A/B Testing & Final Report Prepared by: Muhammad Anas ¦ Date: May 2026 Internship: DevelopersHub Corporation ¦ Deadline: 5th June 2026

Week 3 Overview This final week focuses on analyzing the performance of the Social Connect campaign, conducting A/B tests, identifying underperforming content, applying optimizations, and preparing the final report and presentation with lessons learned and future recommendations.

# Section 1: Campaign Performance Monitoring

## 1.1  Overall Campaign Results — 3-Week Summary

The following metrics represent the complete 3-week campaign performance for Social Connect. Mock data is used based on realistic industry benchmarks for a small-budget app launch campaign.

| 68,400 Total Reach Across all platforms | 112,800 Total Impressions All posts + ads | 542 App Downloads Target was 500 ✓ | 218 Email Sign-ups Target was 200 ✓ |
| --- | --- | --- | --- |

| 13.2% Avg Engagement Rate Target was 5% ✓✓ | 3.4% Avg CTR (Ads) Target was 3% ✓ | 4,320 Total Likes Across all 5 posts | 312% ROI (Mock) $100 spend / $312 value |
| --- | --- | --- | --- |

## 1.2  Week-by-Week Performance Breakdown

| Metric | Week 1 Baseline | Week 2 Results | Week 3 Results | Total / Final |
| --- | --- | --- | --- | --- |
| Reach | 1,200 | 28,500 | 38,700 | 68,400 |
| Impressions | 1,800 | 46,200 | 64,800 | 112,800 |
| Engagement Rate | 2.1% | 8.4% | 13.2% | 13.2% (Final) |
| Post Likes | 89 | 1,845 | 2,386 | 4,320 |
| Comments | 14 | 312 | 489 | 815 |
| Shares | 22 | 567 | 743 | 1,332 |
| Profile Clicks | 67 | 1,234 | 1,876 | 3,177 |
| App Downloads | 45 | 245 | 252 | 542 |
| Email Sign-ups | 18 | 98 | 102 | 218 |
| Ad CTR | 1.2% | 2.8% | 3.4% | 3.4% (Final) |
| Ad CPC (Mock) | $0.62 | $0.48 | $0.41 | $0.41 (Final) |

## 1.3  Platform-Wise Performance

| Platform | Posts Published | Total Reach | Engagement Rate | App Clicks | Best Performing Post |
| --- | --- | --- | --- | --- | --- |
| Instagram | 3 posts + Story Ad | 28,400 | 15.3% | 1,245 | Post 5 — CTA Video Reel |
| Facebook | 2 posts + Feed Ad | 18,200 | 10.7% | 876 | Post 3 — Why Social Connect |
| LinkedIn | 1 post | 6,800 | 7.2% | 312 | Post 3 — Infographic |
| TikTok | 1 video post | 15,000 | 18.6% | 744 | Post 5 — CTA Video |
| Google Ads | Search Ads | — | — | 1,890 | "Download Social Connect" keyword |
| Email | 3 email series | 218 subs | 28.4% open | 467 | Email 1 — Welcome Email |

## 1.4  KPI Achievement Summary

| KPI | Target | Actual Result | Status | Notes |
| --- | --- | --- | --- | --- |
| Brand Awareness (Reach) | 20% increase | 5,600% increase | EXCEEDED | Far exceeded — organic viral reach |
| App Downloads | 500 downloads | 542 downloads | ACHIEVED | 102% of target achieved |
| Engagement Rate | 5% minimum | 13.2% average | EXCEEDED | TikTok drove highest engagement |
| CTR on Ads | 3% | 3.4% | ACHIEVED | Story Ads outperformed Feed Ads |
| CPC | Under $0.50 | $0.41 | ACHIEVED | Cost optimized in Week 3 |
| Email Open Rate | 25% | 28.4% | ACHIEVED | Personalized subject lines worked |
| Email Sign-ups | 200 sign-ups | 218 sign-ups | ACHIEVED | 109% of target achieved |

# Section 2: A/B Testing Results

Three A/B tests were conducted during Week 2 and Week 3 to optimize campaign performance. Each test compared two variants to identify which version drove better results.

## 2.1  A/B Test 1 — Ad Headline Copy

A/B TEST 1 ¦ Facebook/Instagram Ad — Headline Copy VARIANT A "Find Your People. Download Social Connect Free." CTR: 2.1% ¦ CPC: $0.58; VARIANT B "Stop Scrolling. Start Connecting. Download Now." CTR: 3.4% ¦ CPC: $0.41. WINNER: VARIANT B — "Stop Scrolling. Start Connecting." Insight: Action-oriented, emotional language outperforms feature-based headlines. Urgency words like 'Stop' and 'Start' drive 62% higher CTR and 29% lower cost per click.

## 2.2  A/B Test 2 — Instagram Post Visual Style

A/B TEST 2 ¦ Instagram Post — Visual Format VARIANT A "Static Image Post (Product Screenshot)" Reach: 4,200 ¦ Saves: 34 ¦ Shares: 28; VARIANT B "Carousel Post (5 Slides — Feature Highlights)" Reach: 9,800 ¦ Saves: 187 ¦ Shares: 143. WINNER: VARIANT B — Carousel Post Insight: Carousel posts receive 3x more saves and 5x more shares than static images on Instagram. Users engage longer with multi-slide content, signaling strong interest to the algorithm, which boosts organic reach significantly.

## 2.3  A/B Test 3 — Email Subject Line

A/B TEST 3 ¦ Welcome Email — Subject Line VARIANT A "Welcome to Social Connect! Your community awaits." Open Rate: 21.3% ¦ Click Rate: 4.2%; VARIANT B "Muhammad, 347 people are already connecting. Are you in?" Open Rate: 28.4% ¦ Click Rate: 7.8%. WINNER: VARIANT B — Personalized + Social Proof Subject Line Insight: Personalization using the recipient's name combined with social proof (showing a specific number) increased open rates by 33% and click rates by 86%. People respond strongly to FOMO (Fear of Missing Out) messaging.

## 2.4  A/B Testing Summary

| Test | What Was Tested | Winner | Improvement | Apply to Future? |
| --- | --- | --- | --- | --- |
| Test 1 | Ad Headline Copy | Variant B — Emotional/Action | +62% CTR | YES — Use in all future ads |
| Test 2 | Instagram Visual Format | Variant B — Carousel | +3x Saves, Reach | YES — Prioritize carousels |
| Test 3 | Email Subject Line | Variant B — Personalized + FOMO | +33% Open Rate | YES — Always personalize |

# Section 3: Optimization — Underperforming Content

## 3.1  Underperforming Content Identified

| Content | Platform | Issue | Metric | Benchmark |
| --- | --- | --- | --- | --- |
| Post 1 — Static Launch Graphic | Instagram | Low saves, low shares | Engagement: 3.2% | Target: 5% |
| Post 3 — Infographic | LinkedIn | Low click-through | CTR: 0.8% | Target: 2% |
| Ad Creative 1 — Feed Banner | Facebook | High CPC, low CTR | CTR: 2.1%, CPC: $0.58 | Target: 3%, $0.50 |
| Email 2 — Feature Spotlight | Mailchimp | Low click rate | Click Rate: 3.1% | Target: 5% |

## 3.2  Optimization Recommendations

|  | 1. Improve Static Posts — Add Motion & Interactivity Problem Identified: Static image posts (Post 1) showed 3.2% engagement — below the 5% target. No saves or carousel interaction possible. Recommended Fix: Convert all future static posts to Reels or Carousels. Add motion graphics using Canva animations. Include a question sticker or poll in Instagram Stories to boost interaction. Expected Impact: +40–60% engagement rate improvement expected |
| --- | --- |

|  | 2. LinkedIn Content — Add Data & Professional Insights Problem Identified: LinkedIn infographic had only 0.8% CTR. The audience on LinkedIn expects more in-depth, data-driven content. Recommended Fix: Replace visual-only infographics with data-rich articles or LinkedIn document posts (PDF carousels). Include statistics, industry research references, and professional commentary to drive higher click-through. Expected Impact: +150% CTR on LinkedIn expected with document-format posts |
| --- | --- |

|  | 3. Facebook Feed Ad — Switch to Video Format Problem Identified: The static banner ad (Ad Creative 1) had a CTR of 2.1% and CPC of $0.58 — both below target. Facebook's algorithm favors video content. Recommended Fix: Replace the static feed ad with a 15-second video ad showing real app usage with subtitles. Use the winning headline from A/B Test 1: "Stop Scrolling. Start Connecting." Expected Impact: +60% CTR improvement, CPC reduction to $0.35 estimated |
| --- | --- |

|  | 4. Email 2 — Add a Clear Single CTA Button Problem Identified: Email 2 had a click rate of only 3.1%. The email contained too much information and multiple CTAs, causing decision fatigue. Recommended Fix: Redesign Email 2 with ONE clear CTA button: "Update My Interests Now". Remove secondary links. Add a progress bar showing profile completion percentage to motivate action. Expected Impact: +80% click rate improvement using single focused CTA |
| --- | --- |

# Section 4: ROI Analysis & Final Performance Report

## 4.1  Return on Investment (ROI) Calculation

ROI Formula: ROI = (Value Generated - Cost Invested) / Cost Invested x 100 Campaign Cost (Mock): $100 total ad spend Value Generated: → 542 app downloads x $0.50 avg value per download = $271 → 218 email sign-ups x $0.25 avg value per lead = $54.50 → Brand awareness value (68,400 reach) = estimated $86 equivalent → Total Value Generated = $411.50 ROI = ($411.50 - $100) / $100 x 100 = 311.5% ✓ POSITIVE ROI Every $1 spent generated $4.12 in estimated value.

## 4.2  Platform ROI Comparison

| Platform | Budget Spent | Downloads Driven | Leads Generated | Cost Per Result | ROI Rating |
| --- | --- | --- | --- | --- | --- |
| Instagram | $30 (mock) | 189 | 78 | $0.11/result | EXCELLENT |
| TikTok | $15 (mock) | 124 | 34 | $0.10/result | EXCELLENT |
| Google Ads | $30 (mock) | 148 | 56 | $0.15/result | GOOD |
| Facebook | $25 (mock) | 81 | 50 | $0.19/result | GOOD |
| TOTAL | $100 | 542 | 218 | $0.13/result | POSITIVE ROI |

## 4.3  Content Performance Ranking

| Rank | Content | Platform | Key Metric | Performance |
| --- | --- | --- | --- | --- |
| #1 | Post 5 — CTA Video Reel | TikTok + Instagram | Reach: 15,000 ¦ Engagement: 18.6% | BEST |
| #2 | Post 2 — Feature Carousel | Instagram | Saves: 187 ¦ Shares: 143 | EXCELLENT |
| #3 | Ad Creative 2 — Story Ad | Instagram Stories | CTR: 4.2% ¦ CPC: $0.38 | EXCELLENT |
| #4 | Email 1 — Welcome Email | Mailchimp | Open: 28.4% ¦ Click: 7.8% | VERY GOOD |
| #5 | Post 4 — Testimonial Card | All Platforms | Shares: 89 ¦ Comments: 134 | VERY GOOD |
| #6 | Post 3 — Infographic | LinkedIn + Facebook | Reach: 6,800 ¦ CTR: 0.8% | AVERAGE |
| #7 | Ad Creative 1 — Feed Banner | Facebook | CTR: 2.1% ¦ CPC: $0.58 | NEEDS WORK |
| #8 | Post 1 — Launch Graphic | Instagram | Engagement: 3.2% | NEEDS WORK |

# Section 5: Lessons Learned

## 5.1  What Worked Well

The following strategies delivered strong results during the campaign: ✅ Video Content Dominates — Short-form videos (Reels/TikTok) achieved 18.6% engagement, the highest of any content type. Video should be the primary content format going forward. ✅ Carousel Posts Drive Saves — Carousel posts received 3x more saves than static images, significantly boosting algorithmic reach on Instagram. ✅ Personalized Emails Work — Adding the recipient's name and social proof to subject lines increased open rates by 33%. Personalization is non-negotiable. ✅ Emotional Ad Copy Outperforms Feature-Based Copy — "Stop Scrolling. Start Connecting." beat "Find Your People." by 62% in CTR. Emotional hooks beat logical selling points. ✅ Multi-Platform Strategy Multiplied Reach — Repurposing one piece of content across 4+ platforms maximized reach without increasing production cost. ✅ User Testimonials Build Trust — Testimonial post drove the highest comment count, showing that social proof is highly persuasive for app promotion.

## 5.2  What Did Not Work Well

The following areas showed weaker performance and require improvement: ❌ Static Image Posts Underperformed — Single-image posts received less than 4% engagement. They lack the interactivity that modern social media audiences expect. ❌ LinkedIn CTR Was Very Low — Professional audiences on LinkedIn did not respond well to visual-only infographics. They need data-rich, text-based content. ❌ Facebook Feed Ads Had High CPC — At $0.58 per click, Facebook Feed Ads were the most expensive and least efficient format. Video ads are needed. ❌ Email 2 Had Decision Fatigue — Multiple CTAs in one email confused subscribers and lowered click rates. Emails need one clear, focused action. ❌ Posting Frequency Was Inconsistent — Some platforms (LinkedIn, TikTok) had fewer posts than planned. A consistent schedule is critical for algorithm performance.

# Section 6: Recommendations for Future Campaigns

Based on the 3-week campaign analysis, the following 8 recommendations are made for future Social Connect digital marketing campaigns:

| # | Recommendation | Priority | Expected Impact |
| --- | --- | --- | --- |
| 1 | Make video content (Reels, TikTok, YouTube Shorts) the primary format — minimum 60% of all content should be video | HIGH | +50% avg reach increase |
| 2 | Use personalization in all email subject lines — include first name + social proof number always | HIGH | +30% email open rates |
| 3 | Invest more budget in Instagram and TikTok — these platforms delivered the best ROI at lowest CPC | HIGH | +40% ROI improvement |
| 4 | Run monthly A/B tests on ad headlines and email subject lines — never run one version only | HIGH | +20–40% per test improvement |
| 5 | Replace static Facebook ads with 15-second video ads using the winning headline formula | MEDIUM | +60% Facebook ad CTR |
| 6 | Publish LinkedIn articles (1,000+ words) instead of infographics — data and insights drive B2B engagement | MEDIUM | +150% LinkedIn CTR |
| 7 | Add user-generated content (UGC) strategy — encourage real users to share their connection stories with a branded hashtag | MEDIUM | Organic reach multiplier |
| 8 | Build a retargeting campaign targeting users who clicked but did not download — use dynamic ads with personalized app screenshots | LOW | +25% conversion rate |

# Section 7: Final Submission Checklist

All 3-Week Internship Deliverables — Final Checklist for Muhammad Anas WEEK 1 DELIVERABLES: ✓ Market Research Document — Target audience, competitor analysis, channel strategy ✓ SMART Goals — 4 goals with KPIs and mock budget ✓ Content Strategy — Pillars, calendar, post ideas, tools list WEEK 2 DELIVERABLES: ✓ 5 Social Media Posts — Launch, Carousel, Infographic, Testimonial, CTA Video ✓ 2 Ad Creatives — Facebook/Instagram Feed Ad + Instagram Story Ad ✓ Blog Post — "5 Ways Social Connect Is Changing How We Make Friends Online" ✓ Email Campaign — 3-email welcome series (Welcome, Feature, Re-engagement) ✓ Campaign publishing schedule + mock ad setup WEEK 3 DELIVERABLES: ✓ Campaign performance metrics — full 3-week analytics report ✓ 3 A/B Tests completed with results and winners identified ✓ Underperforming content identified with optimization plan ✓ ROI analysis — 311% positive ROI achieved ✓ Lessons learned — what worked, what did not ✓ 7 future recommendations documented ✓ Final presentation outline prepared (15 slides) SUBMISSION TASKS: ✓ All 3 Word documents uploaded to GitHub repository ✓ GitHub repository link submitted on Google Classroom ✓ Work shared on LinkedIn with #DevelopersHub #DigitalMarketing hashtags ✓ Final PowerPoint presentation file ready for submission SUBMISSION DEADLINE: 5th June 2026